## Sheet1
Sprint Burndown Chart For Sprint 3
User Story | Estimation (Hours)
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
As a first time user, i want to set a strong password so that no one can hack my account easily. | Estimation (Hours) Day 0: 60; Estimation (Hours) Day 2: 20; Estimation (Hours) Day 4: 10; Estimation (Hours) Day 6: 15; Estimation (Hours) Day 8: 15
As a user, I want to be able to search for restaurants by their names so that I can find the particular restaurant | Estimation (Hours) Day 0: 55; Estimation (Hours) Day 1: 5; Estimation (Hours) Day 2: 10; Estimation (Hours) Day 4: 10; Estimation (Hours) Day 6: 10; Estimation (Hours) Day 10: 20
As a user I want to have flexible online payment options so that I can choose any method of my choice | Estimation (Hours) Day 0: 50; Estimation (Hours) Day 1: 10; Estimation (Hours) Day 3: 20; Estimation (Hours) Day 5: 10; Estimation (Hours) Day 7: 10
As a restaurant, I want to view the order date, payment mode, items, total price, and user information so that I can decide whether I accept the order or not. | Estimation (Hours) Day 0: 35; Estimation (Hours) Day 2: 5; Estimation (Hours) Day 4: 10; Estimation (Hours) Day 9: 20
Remaining Effort | 200 | 185 | 150 | 130 | 100 | 90 | 65 | 55 | 40 | 20 | 0
Ideal Trend | 200 | 180 | 160 | 140 | 120 | 100 | 80 | 60 | 40 | 20 | 0